## WBS
Create a project from this template on wbsgantt
WBS Code | Task Name | Type | Duration (d) | WEIGHT (%) | Definition
1 | Construction Project | Deliverable |  | 100 | Small-to-mid scale building and facility construction project
1.1 | Initiation & Permits | Phase |  | 10
1.1.1 | Project planning | Work Package | 5 | 40 | Establish project overview, budget, and master schedule
1.1.2 | Permit application & approval | Work Package | 15 | 60 | Apply for and obtain building permits from authorities
1.2 | Design | Phase |  | 15
1.2.1 | Schematic design | Work Package | 10 | 40 | Develop schematic design: layout, scale, structural approach
1.2.2 | Detailed design | Work Package | 15 | 45 | Produce construction-ready drawings and specifications
1.2.3 | Design review & sign-off | Work Package | 4 | 15 | Review design package adequacy and finalize
1.3 | Procurement & Contracting | Phase |  | 12
1.3.1 | Contractor selection & contract | Work Package | 10 | 40 | Tender, evaluate, and contract the builder
1.3.2 | Material procurement | Work Package | 7 | 35 | Order long-lead and key materials, confirm delivery dates
1.3.3 | Site mobilization prep | Work Package | 5 | 25 | File commencement report, set up site office and safety plan
1.3.4 | Construction start | Milestone | 0 | 0 | Point at which site works begin
1.4 | Construction | Phase |  | 45
1.4.1 | Temporary works | Work Package | 7 | 10 | Install hoarding, scaffolding, and site facilities
1.4.2 | Foundation & structural frame | Work Package | 25 | 35 | Excavation, foundation, and structural frame construction
1.4.3 | MEP works | Work Package | 20 | 25 | Mechanical, electrical, and plumbing installation
1.4.4 | Finishing works | Work Package | 18 | 25 | Interior finishes: painting, flooring, windows and doors
1.4.5 | External & ancillary works | Work Package | 8 | 5 | External paving, landscaping, and ancillary facilities
1.5 | Quality & Inspection | Phase |  | 8
1.5.1 | Quality & safety inspections | Work Package | 6 | 40 | Verify quality and safety compliance, rectify findings
1.5.2 | Commissioning | Work Package | 5 | 30 | Test-run mechanical and electrical systems, verify performance
1.5.3 | Completion inspection | Work Package | 5 | 30 | Apply for and undergo the authority completion inspection
1.5.4 | Completion inspection passed | Milestone | 0 | 0 | Point at which the authority completion inspection is passed
1.6 | Handover & Closure | Phase |  | 10
1.6.1 | Defect rectification | Work Package | 7 | 35 | Rectify remaining defects and incomplete items
1.6.2 | Closeout documents & final account | Work Package | 6 | 35 | Compile as-built documents and settle the final account
1.6.3 | Facility handover | Work Package | 4 | 30 | Hand over the facility and operating documentation, brief users
1.6.4 | Project completion | Milestone | 0 | 0 | Works closed out and project complete