## WBS
Create a project from this template on wbsgantt
WBS Code | Task Name | Type | Duration (d) | WEIGHT (%) | Definition
1 | In-house Development | Deliverable |  | 100 | In-house system development project
1.1 | Requirements | Phase |  | 15
1.1.1 | Current-state analysis & problem definition | Work Package | 4 | 40 | Assess current business processes and systems
1.1.2 | Requirements gathering & definition | Work Package | 4 | 35 | Elicit functional and non-functional requirements via interviews and workshops
1.1.3 | Scope finalization & prioritization | Work Package | 3 | 25 | Clarify in-scope / out-of-scope and set development priorities
1.2 | Analysis & Design | Phase |  | 20
1.2.1 | Business process analysis | Work Package | 5 | 30 | Model AS-IS / TO-BE business processes
1.2.2 | System architecture design | Work Package | 5 | 35 | Design tech stack, deployment topology, and security architecture
1.2.3 | UI/UX design | Work Package | 6 | 35 | Design screens and user flows
1.3 | Development | Phase |  | 30
1.3.1 | DB design & build | Work Package | 7 | 20 | Finalize ERD, create schema, indexes, and migrations
1.3.2 | Backend API development | Work Package | 14 | 35 | Implement business logic, REST API, and authentication modules
1.3.3 | Frontend development | Work Package | 14 | 30 | Implement UI based on screen designs and integrate APIs
1.3.4 | Infrastructure & deployment pipeline setup | Work Package | 5 | 15 | Server provisioning, CI/CD setup, and environment configuration (dev/stg/prod)
1.4 | Integration Testing | Phase |  | 20
1.4.1 | Integration & regression testing | Work Package | 7 | 50 | End-to-end integration testing and defect resolution
1.4.2 | Performance & security testing | Work Package | 5 | 30 | Load testing and vulnerability scanning
1.4.3 | UAT (User Acceptance Testing) | Work Package | 5 | 20 | Direct testing and sign-off by business users
1.5 | User Training | Phase |  | 8
1.5.1 | Training material development | Work Package | 3 | 40 | Create user manuals and video tutorials
1.5.2 | Training delivery | Work Package | 5 | 60 | Conduct system usage training for business users
1.6 | Stabilization | Phase |  | 7
1.6.1 | Operations handover & hypercare | Work Package | 10 | 60 | Handover to operations team and hypercare support
1.6.2 | Stabilization complete | Work Package | 5 | 40 | End of stabilization period and project closure