## WBS
Create a project from this template on wbsgantt
WBS Code | Task Name | Type | Duration (d) | WEIGHT (%) | Definition
1 | New-Product MVP | Deliverable |  | 100 | Lean product for market validation
1.1 | Discovery & Definition | Phase |  | 25
1.1.1 | Market & competitive research | Work Package | 5 | 35 | Market and competitive analysis
1.1.2 | User interviews | Work Package | 4 | 30 | Target user interviews
1.1.3 | Product Requirements Document (PRD) | Work Package | 5 | 35 | Draft PRD
1.2 | Design | Phase |  | 25
1.2.1 | UX wireframes | Work Package | 5 | 30 | Wireframes for the core screen flows
1.2.2 | UI design | Work Package | 6 | 35 | Visual UI design based on the wireframes
1.2.3 | Technical architecture design | Work Package | 6 | 35 | Tech stack and system structure decisions
1.3 | MVP Development | Phase |  | 30
1.3.1 | Backend API | Work Package | 12 | 35 | Backend APIs for the core features
1.3.2 | Frontend | Work Package | 12 | 35 | Frontend for the core screens
1.3.3 | Core feature integration | Work Package | 8 | 30 | Backend-frontend integration for core scenarios
1.4 | QA & Launch | Phase |  | 20
1.4.1 | Integration testing | Work Package | 7 | 100 | Integration / regression testing
1.4.2 | Official launch | Milestone | 0 | 0 | The MVP launch point