## WBS
Create a project from this template on wbsgantt
WBS Code | Task Name | Type | Duration (d) | WEIGHT (%) | Definition
1 | Marketing Campaign | Deliverable |  | 100 | Integrated marketing campaign from planning to results reporting
1.1 | Campaign Planning | Phase |  | 20
1.1.1 | Goals & KPI definition | Work Package | 4 | 30 | Define campaign goals and measurable KPIs
1.1.2 | Audience & messaging strategy | Work Package | 5 | 40 | Define target segments and design key messages
1.1.3 | Budget & channel mix | Work Package | 3 | 30 | Allocate budget across channels and fix the flight schedule
1.2 | Creative Production | Phase |  | 30
1.2.1 | Copywriting | Work Package | 5 | 25 | Write copy and headlines per channel
1.2.2 | Design & banner production | Work Package | 8 | 35 | Produce key visual and per-channel banner sizes
1.2.3 | Video production | Work Package | 10 | 25 | Shoot and edit campaign video
1.2.4 | Creative review & sign-off | Work Package | 3 | 15 | Brand and legal review, final sign-off
1.3 | Channel Setup | Phase |  | 15
1.3.1 | Media booking & account setup | Work Package | 4 | 35 | Set up ad accounts and campaign structure, book placements
1.3.2 | Landing page build | Work Package | 6 | 40 | Build and QA the campaign landing page
1.3.3 | Tracking & conversion setup | Work Package | 3 | 25 | Configure and verify conversion events, pixels, and UTM scheme
1.3.4 | Campaign launch | Milestone | 0 | 0 | Point at which the campaign goes live
1.4 | Execution & Optimization | Phase |  | 25
1.4.1 | Launch & initial monitoring | Work Package | 5 | 30 | Monitor impressions, clicks, and conversions right after launch
1.4.2 | Creative & bid optimization | Work Package | 15 | 40 | Rotate creatives and rebalance bids and budget on performance
1.4.3 | Mid-campaign review | Work Package | 2 | 30 | Share interim results and decide direction for the remainder
1.4.4 | Campaign end | Milestone | 0 | 0 | Point at which all channels stop running
1.5 | Analysis & Reporting | Phase |  | 10
1.5.1 | Data & performance analysis | Work Package | 4 | 45 | Aggregate channel data and analyze KPI attainment
1.5.2 | Results report | Work Package | 3 | 35 | Write the results report: performance, learnings, spend
1.5.3 | Retrospective & next-step recommendations | Work Package | 2 | 20 | Run the retrospective and record recommendations for the next campaign
1.5.4 | Results reported | Milestone | 0 | 0 | Results reported and the campaign closed