## WBS
Create a project from this template on wbsgantt
WBS Code | Task Name | Type | Duration (d) | WEIGHT (%) | Definition
1 | SI Delivery | Deliverable |  | 100 | System delivery project based on standard SI methodology
1.1 | Initiation | Phase |  | 8
1.1.1 | Project initiation preparation | Work Package | 4 | 55 | Establish project charter, organization, and schedule plan
1.1.2 | Kickoff report | Work Package | 3 | 45 | Kickoff presentation and alignment with stakeholders
1.2 | Analysis | Phase |  | 15
1.2.1 | Current-state survey & As-Is analysis | Work Package | 6 | 40 | Analyze current systems and business processes
1.2.2 | Requirements definition | Work Package | 5 | 35 | Gather and document functional and non-functional requirements
1.2.3 | Analysis deliverables review | Work Package | 3 | 25 | Quality review of analysis phase deliverables
1.3 | Design | Phase |  | 20
1.3.1 | Architecture design | Phase |  | 45
1.3.1.1 | System architecture design | Work Package | 5 | 55 | Design HW, SW, and network architecture
1.3.1.2 | DB design | Work Package | 5 | 45 | Design logical and physical data models
1.3.2 | Functional design | Phase |  | 55
1.3.2.1 | Screen design | Work Package | 5 | 50 | UI/UX screen design and prototyping
1.3.2.2 | Interface design | Work Package | 5 | 50 | Define interfaces for external system integration
1.4 | Development | Phase |  | 30
1.4.1 | Common module development | Work Package | 10 | 20 | Develop authentication, authorization, and common components
1.4.2 | Core feature development | Work Package | 20 | 40 | Implement core business functions
1.4.3 | Interface development | Work Package | 12 | 25 | Develop external system integrations
1.4.4 | Environment setup & deployment | Work Package | 7 | 15 | Configure server environments and build deployment pipeline
1.5 | Integration & Migration | Phase |  | 18
1.5.1 | Integration testing | Work Package | 10 | 40 | End-to-end integration testing and defect resolution
1.5.2 | Performance & security testing | Work Package | 7 | 30 | Load testing and security vulnerability assessment
1.5.3 | Data migration | Work Package | 7 | 30 | Migrate and validate data from legacy systems
1.5.4 | Interim acceptance complete | Milestone | 0 | 0 | Client interim acceptance of integration and migration deliverables
1.6 | Go-live & Stabilization | Phase |  | 9
1.6.1 | System go-live | Work Package | 3 | 50 | Final production deployment and service launch
1.6.2 | Hypercare & stabilization | Work Package | 10 | 50 | Post-go-live intensive support and defect resolution
1.6.3 | Final acceptance complete | Milestone | 0 | 0 | Final acceptance and project closure point